## Sheet1
Games, Animation and VFX Skills Extended Diploma Year 2
Initial risk scoring:
Risk Assessment Point
Risk | Responsibility | (P) Factor | (I) factor | Risk Points
Talent on team | Producer | 20% | 20% | 4 |  | Risk Points breakdown:
Team ability to produce assets | Team Supervisors | 20% | 40% | 8
Team ability to produce code | Team Supervisors | 40% | 40% | 16
Community - relationships between team members | Team Supervisors | 20% | 20% | 4 |  | 0 - 99 | Very Low Risk
Time Management - meeting deadlines | Producer | 40% | 60% | 24 |  | 100 - 150 | Low Risk
Depth of Gameplay | Lead Designer | 20% | 40% | 8 |  | 150 - 200 | Medium Risk
Clear gameplay loop | Lead Designer | 20% | 40% | 8 |  | 200 - 250 | High Risk
Clear Visual Style | Art Lead | 20% | 20% | 4 |  | 300+ | Unworkable
Learning Potential - Classes | Tutors / College | 20% | 20% | 4
Absence / Illness or other | Team Members | 40% | 40% | 16
College Closure | College | 20% | 80% | 16
Loss of work - IT failures | College / Producer | 20% | 40% | 16
|  |  | Total: | 128
Key: |  |  | IMPACT (i)
PROBABILITY (p) | 20% | 40% | 60% | 80% | 100%
20% | 4 | 8 | 12 | 16 | 20
40% | 8 | 16 | 24 | 32 | 40
60% | 12 | 24 | 36 | 48 | 60
80% | 16 | 32 | 48 | 64 | 80
100% | 20 | 40 | 60 | 80 | 100
Use this form to calculate a risk value for your teams production - After your initial scoring, you should add in mitigation factors to help reduce the Risk value of the project - | Your aim must be within the Medium to Low Risk banding
Risk Mitigation Plans
Risk highligheted | Mitigation Plan
Talent on team | Talk with the tutor and discuss which people in class will be sorted into teams.
Team ability to produce assets | If member of the team is struggeling to produce assets, have multiple members work on asset production.
Team ability to produce code | If team struggled to produce code effceintly, discuss with team the possibility of sharing the job role and giving the struggeling member help.
Community - relationships between team members | Play games with team members after work day is over to create a team bond and to destress. Keep good communication between the team.
Time Management - meeting deadlines | Ensure the team meets deadlines by constantly checking up with progress with team.
Depth of Gameplay | The team will need to discuss how we will create in depth of game play within our game and make it an enjoyable experience for everyone.
Clear gameplay loop | Discuss with team to organise a clear gameplay loop that would be easy to understand.
Clear Visual Style | Work with team and art director to develop a clear style that would be enjoyable for the player.
Learning Potential - Classes | We will need use our time as a group to learn as much as possible with the time we have.
Absence / Illness or other | Team members will need to ensure that work can be continued by other team members if illor absent.
College Closure | Discuss the options avalible with tutor and how we will combat this issue.
Loss of work - IT failures | Have saftey nets prepare, e.g. save copies of work to a USB and external file storage software such as Onedrive or Dropbox.
Revised Risk Scoring
Risk Assessment Point
Risk | Responsibility | (P) Factor | (I) factor | Risk Points
Talent on team | Producer | 20% | 20% | 4 |  | Risk Points breakdown:
Team ability to produce assets | Team Supervisors | 20% | 40% | 8
Team ability to produce code | Team Supervisors | 20% | 40% | 8
Community - relationships between team members | Team Supervisors | 40% | 80% | 32 |  | 0 - 99 | Very Low Risk
Time Management - meeting deadlines | Producer | 40% | 60% | 24 |  | 100 - 150 | Low Risk
Depth of Gameplay | Lead Designer | 20% | 20% | 4 |  | 150 - 200 | Medium Risk
Clear gameplay loop | Lead Designer | 20% | 20% | 4 |  | 200 - 250 | High Risk
Clear Visual Style | Art Lead | 20% | 20% | 4 |  | 300+ | Unworkable
Learning Potential - Classes | Tutors / College | 20% | 20% | 4
Absence / Illness or other | Team Members | 40% | 20% | 8
College Closure | College | 80% | 40% | 32
Loss of work - IT failures | College / Producer | 20% | 60% | 12
|  |  | Total: | 144
Key: |  |  | IMPACT (i)
PROBABILITY (p) | 20% | 40% | 60% | 80% | 100%
20% | 4 | 8 | 12 | 16 | 20
40% | 8 | 16 | 24 | 32 | 40
60% | 12 | 24 | 36 | 48 | 60
80% | 16 | 32 | 48 | 64 | 80
100% | 20 | 40 | 60 | 80 | 100